## Sheet1
Task ID | Task Name | Duration (days) | Start Date | Finish Date | Predecessors | Resource
1 | [Research & Planning] Tourism Market Research | 8 | 2025-11-03 | 2025-11-11 |  | IT Team
2 | [Research & Planning] Stakeholder Consultation | 10 | 2025-09-20 | 2025-09-30 | 1 | Marketing Team
3 | [Research & Planning] Feasibility Study | 7 | 2025-10-09 | 2025-10-16 | 1,2 | Marketing Team
4 | [Research & Planning] Approval from Authorities | 11 | 2025-11-17 | 2025-11-28 | 1,3,2 | Manager
5 | [Infrastructure & Setup] Office Location Selection | 10 | 2025-11-04 | 2025-11-14 | 4 | Consultants
6 | [Infrastructure & Setup] Lease Agreement | 7 | 2025-11-29 | 2025-12-06 | 5 | Consultants
7 | [Infrastructure & Setup] Interior Design | 17 | 2025-09-11 | 2025-09-28 | 2,6 | Finance Dept
8 | [Infrastructure & Setup] Equipment Purchase | 10 | 2025-09-03 | 2025-09-13 | 1,2,3 | Finance Dept
9 | [Infrastructure & Setup] Network Setup | 10 | 2025-11-25 | 2025-12-05 | 7 | HR Department
10 | [Infrastructure & Setup] Booking Software Integration | 16 | 2025-09-07 | 2025-09-23 | 8 | HR Department
11 | [Staffing & Training] Recruitment Campaign | 20 | 2025-10-16 | 2025-11-05 | 5 | IT Team
12 | [Staffing & Training] Interview Process | 10 | 2025-11-06 | 2025-11-16 | 8,4,9 | IT Team
13 | [Staffing & Training] Onboarding Staff | 12 | 2025-09-11 | 2025-09-23 |  | HR Department
14 | [Staffing & Training] Tour Guide Training | 6 | 2025-09-15 | 2025-09-21 | 5 | Consultants
15 | [Staffing & Training] Customer Service Training | 7 | 2025-10-05 | 2025-10-12 | 3 | Consultants
16 | [Marketing & Partnerships] Brand Identity Design | 19 | 2025-09-30 | 2025-10-19 |  | Manager
17 | [Marketing & Partnerships] Website Development | 12 | 2025-11-18 | 2025-11-30 | 7,6 | HR Department
18 | [Marketing & Partnerships] Social Media Setup | 5 | 2025-09-24 | 2025-09-29 |  | Consultants
19 | [Marketing & Partnerships] Advertising Campaign | 12 | 2025-11-07 | 2025-11-19 |  | Tour Guides
20 | [Marketing & Partnerships] Partnership Agreements | 7 | 2025-11-01 | 2025-11-08 |  | Tour Guides
21 | [Operations & Launch] Test Booking System | 14 | 2025-10-16 | 2025-10-30 | 6,7 | HR Department
22 | [Operations & Launch] Soft Opening | 6 | 2025-10-31 | 2025-11-06 | 17,18 | Tour Guides
23 | [Operations & Launch] Collect Feedback | 17 | 2025-11-13 | 2025-11-30 | 12 | HR Department
24 | [Operations & Launch] Grand Opening | 14 | 2025-09-10 | 2025-09-24 | 23,22,2 | Tour Guides
25 | [Operations & Launch] Post-launch Review | 6 | 2025-10-05 | 2025-10-11 | 20,4,15 | Tour Guides
26 | Project Kickoff | 0 | 2025-09-01 | 2025-09-01 |  | Manager
27 | Feasibility Approved | 0 | 2025-10-01 | 2025-10-01 | 3 | Consultants
28 | System Ready | 0 | 2025-11-15 | 2025-11-15 | 12,13 | IT Team
29 | Grand Opening Event | 0 | 2025-12-15 | 2025-12-15 | 22 | Marketing Team